## Sheet1
Client | iLeaf Technology
Project Name | Project A
Frequency | Repeateative
| Monthly 4 |  | BLOG Writing | Graphics Design | Website Development
| Project Manager |  | Mr. Mustafa
| Team |  | Arbaaz, Sunil
| Deliverables 1 |  | Week 1 (1 Jan to 7th Jan) | Add Task Button |  |  |  |  | Activity Management | CRM | Project Management | Task
|  | Task 1 | Subject Identification & Finalization | Standard Table | Option- table / Manual Enter |  | Add Activity Button | Woking Data | User add activity | User add activity | User add activity | Applicable Properties
[9 empty] | admin add activity | admin add activity | admin add activity
|  |  | Activity 1 (Vist Client and finalize the subject) | Sunil | Date | Time | Status | View | transfer | transfer | transfer
|  |  | Activity 2 (Finalize the Name from Client on Mail ) | Arbaaz | Date | Time | Status |  | reschedule | reschedule | reschedule
|  | Task 2 | Data Collection | Standard Table |  |  |  |  | User Activity Page
Collective data
|  | Task 3 | Draft presentation & Finalization | Standard Table
Delvierable 2
Delvierable 3
Delvierable 4

## Sheet2
Project 1 |  |  |  | Task Name | Start date | End date | Extension by | Updated date | Status | Expand
1 | Delivery 1 |  | 1 week |  | 2021-01-01 | 2021-01-07 | 3 | 2021-01-10
Activity 1
Activity 2
Activity 3
2 | Delivery 2 |  | 2 week |  | 2021-01-11 | 2021-01-17 | -2 | 2021-01-15
Activity 1
Activity 2
Activity 3
Activity 4
4 | Delivery 3 |  | 3 week |  | 2021-01-16 | 2021-01-22 | 0 | 2021-01-22
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
3 | Delivery 4 |  | 4 week |  | 2021-01-23 | 2021-01-29 | 0 | 2021-01-29
Activity 1
Activity 2
Activity 3
Activity 4
Activity 5
Formulas:
End date = [Start date]+6
Updated date = [End date]+[Extension by]